PROJECT JASPER

Post-Wildfire Environmental Digital Twin & AI Monitoring System

Implementation Plan

Architecture, Scope, Digital Twin Model & Sprint Breakdown

| Document ID | JASPER-IMPL-001 |
| --- | --- |
| Version | v1.0 |
| Prepared By | Edwin Olaez — PM & Lead QA/Security Engineer |
| Project Start | June 9, 2026 |
| Deadline | August 3, 2026 |
| Stakeholders | SAIT Faculty, SAIT CERCUTS |
| Status | DRAFT — Awaiting Review |

1. Stakeholders

Project Jasper is a prototype system with real-world handoff intent. Two primary stakeholder groups govern acceptance criteria and dashboard requirements.

| Stakeholder | Organization | Role in Project | What They Need to See |
| --- | --- | --- | --- |
| SAIT Faculty / Academic Supervisors | SAIT | Academic evaluation and grade sign-off | Scope completion, documentation quality, sprint delivery, code standards |
| SAIT CERCUTS Research Centre | SAIT | Research partner; environmental data consumer | Digital twin accuracy, AI model outputs, environmental risk data, pipeline reliability |
| Edwin Olaez | Project Team | PM + Lead QA/Security Engineer | Sprint velocity, integration health, security gate status, test completion |
| Feven | Project Team | Data Pipeline & API Engineer | Ingest pipeline status, Kong Gateway health, data flow logs |
| Richard | Project Team | AI/ML & Simulation Specialist | Model training metrics, simulation accuracy, contaminant tracking outputs |
| Reyta | Project Team | Frontend GIS Developer | Map render performance, UI test results, API response times |
| Rahil | Project Team | Full-Stack Data & Analytics Engineer | DB query performance, RBAC audit logs, server load metrics |

Note: Parks Canada and the Town of Jasper are downstream beneficiaries of this research. They are not active project stakeholders at the prototype stage but represent the real-world handoff audience. CERCUTS acts as the bridge between this prototype and those agencies.

2. Scope of Work

Project Jasper is framed as a working prototype with real-world handoff intent. Think of it as opening a new restaurant concept: we are building and running a fully operational pilot location, not a mock-up — but we acknowledge it is a first store, not a national rollout.

## 2.1 In Scope

- Environmental Digital Twin prototype for the Athabasca River headwaters and wildfire-affected zones surrounding Jasper, Alberta

- Integration of pre- and post-fire satellite imagery (GeoTIFF), Digital Elevation Model (DEM) terrain data, and water quality telemetry datasets

- AI-powered change-detection machine learning model for identifying post-fire landscape shifts

- Mathematical simulation of rainfall, erosion risk, and hydrocarbon/contaminant movement

- GIS visualization dashboard with temporal filtering, sector querying, and environmental risk overlays

- Unified geospatial database (Supabase + PostGIS) with role-based access control

- Operational reporting and server load metrics via Prometheus

- CI/CD pipeline with automated security scanning (Semgrep, Dependabot)

- Full technical documentation: README, AGENTS.md, API contracts, deployment runbook

- CERCUTS supplemental dataset integration where data is made available

## 2.2 Out of Scope

- Drone hardware procurement or physical field data collection — remote sensing data only

- Real-time live sensor integration beyond simulated/available datasets at prototype stage

- Mobile native app development — web-responsive only

- Official Parks Canada system integration or production API handoff — prototype handoff document only

- Long-term infrastructure hosting costs beyond the project window

- Legal or regulatory environmental certification of model outputs

3. Digital Twin Model

A digital twin is a live, data-connected virtual replica of a physical system. In QSR terms: imagine being able to see your entire restaurant — every fryer temperature, every queue length, every inventory level — on a single screen in real time, and also run "what if" simulations without touching the actual restaurant. That is exactly what this digital twin does for the Athabasca River watershed.

## 3.1 What the Digital Twin Represents

| Twin Component | Physical Reality It Mirrors | Data Source | Owner |
| --- | --- | --- | --- |
| Terrain & Elevation Layer | Physical landscape, slopes, ridgelines, river channels | DEM (Digital Elevation Model) tiles | Feven (ingest), Rahil (store) |
| Vegetation & Burn Scar Layer | Pre/post-fire vegetation coverage and burn extent | Satellite GeoTIFF imagery | Feven (ingest), Richard (ML detection) |
| Hydrology Layer | River flow paths, watershed drainage, flood zones | DEM + hydrological formulas | Richard (simulation) |
| Erosion Risk Layer | Soil destabilization probability after wildfire | Rainfall formula + slope analysis | Richard (simulation) |
| Contaminant Tracking Layer | Hydrocarbon / sediment plume movement in river system | Water quality telemetry + vector model | Richard (model), Feven (telemetry) |
| Water Quality Layer | Real or simulated water monitoring sensor readings | Telemetry stream / CERCUTS datasets | Feven (ingest), Rahil (store) |
| Risk Zone Overlay | Combined environmental hazard probability map | Aggregated ML + simulation outputs | Reyta (visualize), Rahil (query) |

## 3.2 Digital Twin Data Flow

Raw environmental data enters at the bottom and surfaces as actionable intelligence at the top — like raw ingredients becoming a finished dish on the customer tray.

| Layer | What Happens | Technology |
| --- | --- | --- |
| Raw Data Sources | Satellite imagery (GeoTIFF), DEM terrain tiles, telemetry streams, CERCUTS datasets ingested | Python FastAPI microservices, Kong Gateway |
| Data Processing | Format parsing, coordinate normalization, spatial indexing, schema validation | PostGIS, Supabase, Python |
| AI/ML Engine | Change-detection model runs on imagery pairs; erosion/rainfall simulations execute; contaminant vectors computed | scikit-learn / TensorFlow, NumPy, SciPy |
| Geospatial Database | All layers stored as spatial records with RBAC; queryable by sector, date range, risk threshold | Supabase + PostGIS |
| API Layer | Single-entry REST API serves processed layers to frontend; rate-limited and authenticated | FastAPI + Kong Gateway |
| GIS Dashboard | Interactive map with temporal slider; sector querying; color-coded risk overlays; reporting widgets | Next.js 14 + React-Leaflet |

4. Dashboard Specification

The GIS Dashboard is what stakeholders (SAIT Faculty, CERCUTS) will actually look at during reviews and presentations. Every widget maps directly to a project deliverable. Think of it as the restaurant's digital operations board — at a glance, you see everything that matters.

## 4.1 Dashboard Panels

| Panel | What It Shows | Audience | Data Source | Owner |
| --- | --- | --- | --- | --- |
| Interactive Map | Full GIS map of Athabasca watershed with base tiles, sector grid, and zoom/pan | All | React-Leaflet + tile server | Reyta |
| Temporal Slider | Slide through pre-fire vs post-fire dates to compare landscape change | CERCUTS, Faculty | Satellite imagery by date | Reyta + Feven |
| Burn Scar Overlay | Color-coded burn extent mapped over terrain; togglable layer | CERCUTS, Faculty | ML change-detection output | Reyta + Richard |
| Erosion Risk Heatmap | High/medium/low erosion probability zones across the watershed | CERCUTS | Rainfall/slope simulation | Reyta + Richard |
| Contaminant Plume Tracker | Animated vector showing projected hydrocarbon movement through river system | CERCUTS, Faculty | Contaminant tracking model | Reyta + Richard |
| Water Quality Indicators | Sensor reading gauges (turbidity, pH, hydrocarbon levels) per monitoring sector | CERCUTS | Telemetry stream / DB | Reyta + Rahil |
| Sector Query Panel | Click a map sector to get all environmental data for that coordinate zone | All | PostGIS spatial query API | Reyta + Rahil |
| Pipeline Status Panel | Shows last successful ingest timestamp, record count, and pipeline health | Edwin (PM), Faculty | Prometheus metrics | Rahil |
| Model Performance Widget | Displays ML model accuracy score (F1), last training date, prediction confidence | Faculty, CERCUTS | Model metadata DB table | Richard + Rahil |
| Sprint/Milestone Tracker | Live milestone completion status visible during faculty reviews | Faculty, Edwin | Project board integration or manual update | Edwin |

5. Project Milestones

Milestones are named delivery gates — not just sprint end-dates. Each milestone has a clear pass/fail criteria. Like a restaurant grand opening checklist: either you're ready to open or you're not.

| # | Milestone Name | Target Date | Exit Criteria | Sign-Off |
| --- | --- | --- | --- | --- |
| M0 | Project Kickoff & Plan Sign-Off | June 9, 2026 | All four plans reviewed and approved by team; repo initialized; roles confirmed | Edwin (PM) |
| M1 | Environment & Foundation Ready | June 20, 2026 | Repo, DB schema, Next.js scaffold, FastAPI scaffold, Kong config, and CI pipeline all operational | Edwin (PM) |
| M2 | Core Data Pipeline Live | July 4, 2026 | GeoTIFF + DEM + telemetry ingest working end-to-end; data visible in Supabase; API routes responding | Edwin + Feven |
| M3 | AI Models & Simulation Operational | July 18, 2026 | Change-detection model trained with baseline F1; erosion + contaminant simulation producing outputs; risk overlays rendering on map | Edwin + Richard |
| M4 | Full System Integration & Staging Deploy | July 25, 2026 | All components integrated; staging URL live; full user journey tested; 0 HIGH security findings | Full Team |
| M5 | Production Deployment & Final Delivery | August 1, 2026 | Production URL live; all documentation complete; stakeholder demo rehearsed | Edwin (PM) |
| M6 | Final Presentation to SAIT Faculty & CERCUTS | August 3, 2026 | Live demo delivered; Q&A completed; handoff documentation submitted | Edwin (PM) |

6. Sprint Plan (June 9 – August 1, 2026)

Four two-week sprints, each scoped to deliver a complete, testable increment. Think of each sprint as a training week before opening day — by the end of each one, something real works.

## Sprint 1 — Foundation  |  June 9 – June 20  |  Milestone: M1

| Task | Owner | Deliverable |
| --- | --- | --- |
| Initialize GitHub repo, branching rules, PR template with security checklist | Edwin | Repo live, branch strategy documented |
| Set up Supabase project + PostGIS extension + RBAC roles | Rahil | DB schema v1 with 4 roles configured |
| Scaffold Next.js 14 + TypeScript + React-Leaflet base map | Reyta | Map shell renders Leaflet tiles at localhost |
| Scaffold FastAPI project + Kong Gateway config + health endpoint | Feven | API responds at /health through Kong |
| Set up ML Python environment + spike change-detection notebook | Richard | Prototype notebook with sample imagery |
| Configure Semgrep + Dependabot + GitHub Actions CI pipeline | Edwin | CI runs lint + security scan on every push |

## Sprint 2 — Core Pipeline  |  June 23 – July 4  |  Milestone: M2

| Task | Owner | Deliverable |
| --- | --- | --- |
| GeoTIFF + DEM ingest microservice parsing real satellite tiles | Feven | Parser reads tiles and stores to PostGIS |
| Water quality telemetry stream parser (live or CERCUTS simulated feed) | Feven | Telemetry records in Supabase table |
| PostGIS spatial queries + sector coordinate querying API endpoint | Rahil | API returns environmental data by sector |
| Train change-detection ML model v1 on pre/post imagery pairs | Richard | F1-score baseline documented in model card |
| Temporal slider UI + sector selection on GIS map | Reyta | Map filters data by date range and sector |
| End-to-end integration test: ingest to DB to API to map | Edwin | Integration test report — full data flow confirmed |

## Sprint 3 — AI Simulation & Visualization  |  July 7 – July 18  |  Milestone: M3

| Task | Owner | Deliverable |
| --- | --- | --- |
| Rainfall + erosion formula simulation on DEM terrain data | Richard | Erosion risk scores stored per sector |
| Hydrocarbon / contaminant vector tracking model | Richard | Plume movement vectors stored in PostGIS |
| Risk-zone color overlays on GIS map (burn scar, erosion, contaminant) | Reyta | Togglable hazard layers on Leaflet map |
| Multi-source data fusion API endpoint (returns all layers for a sector) | Feven | Single endpoint returns fused environmental data |
| Prometheus metrics + pipeline health + model performance widgets | Rahil | Dashboard panels showing pipeline and model status |
| Full vulnerability scan sweep — 0 HIGH findings required | Edwin | Semgrep report attached to Sprint 3 review |

## Sprint 4 — Hardening & Delivery  |  July 21 – August 1  |  Milestones: M4, M5

| Task | Owner | Deliverable |
| --- | --- | --- |
| Full regression test suite + test completion report | Edwin | Signed-off test completion report |
| UI responsiveness optimization — mobile/tablet pass | Reyta | Lighthouse performance score 85+ |
| Vercel production deploy + Cloudflare CDN configuration | Feven | Live production URL accessible |
| Final DB performance tuning — query time under 500ms | Rahil | Query benchmark report |
| ML model final validation + model card + accuracy report | Richard | Model card submitted to CERCUTS |
| README + AGENTS.md + API docs + deployment runbook complete | Edwin | Full documentation package submitted |
| Stakeholder demo rehearsal with full team | Edwin (PM) | Demo script rehearsed; Q&A prepared |

7. Integration Strategy & Team Coordination

Every team member works on a different "station" — just like a QSR kitchen. The PM's job is to make sure what comes off one station is exactly what the next station is expecting. Integration contracts prevent surprises.

## 7.1 API Contracts (agreed before Sprint 2 begins)

| From | To | Contract Item | Deadline |
| --- | --- | --- | --- |
| Feven | Rahil | JSON schema for ingest records: field names, types, coordinate format, timestamps | June 20 (M1) |
| Feven | Reyta | REST endpoint spec: URL, auth header, response shape for all map data queries | June 20 (M1) |
| Richard | Rahil | ML output schema: risk_score, contaminant_vector, simulation_type, timestamp fields | June 20 (M1) |
| Rahil | Reyta | Supabase query spec or real-time subscription shape for dashboard widgets | June 20 (M1) |
| All | Edwin | PR review: security checklist completed, unit tests passing, integration test sign-off | Ongoing |

## 7.2 Definition of Done

- Code committed and CI pipeline passes (lint, build, security scan)

- Unit tests written and passing for all new code

- Peer code review completed and approved by at least one teammate

- API contract or interface documented if the task creates a new integration point

- Edwin has verified the integration test for that component before marking Done

## 7.3 Git Branching

| Branch | Purpose | Merge Rule |
| --- | --- | --- |
| main | Production-ready only | Edwin approval + passing CI required |
| develop | Integration branch — all features land here first | Peer review by 1 teammate required |
| feature/[owner]-[ticket] | Individual work per sprint ticket | PR to develop only; never direct to main |
| hotfix/[issue] | Critical patches | Edwin approval; merges to main AND develop |

8. Risk Register

| Risk | Likelihood | Impact | Mitigation |
| --- | --- | --- | --- |
| Real satellite / CERCUTS data unavailable on schedule | Medium | High | Use USGS / ESA open datasets and synthetic data as fallback; confirm with CERCUTS by June 20 |
| ML model accuracy below acceptable threshold | Medium | High | Baseline F1 set in Sprint 2; iterate in Sprint 3; Richard escalates to Edwin if blocked |
| Integration delays between team members | Medium | High | All API contracts finalized at M1; Edwin gates integration test before Sprint 3 |
| Kong Gateway configuration complexity blocks pipeline | Low | Medium | Feven spikes Kong in Sprint 1 before any downstream dependency is built |
| PostGIS spatial query performance at scale | Low | Medium | Spatial indices created Sprint 2; Rahil benchmarks in Sprint 3 |
| Scope creep on AI simulation features | High | Medium | Richard scoped to 2 simulation deliverables; PM holds scope change log; no additions after M2 |
| Team member unavailability near deadline | Medium | High | Edwin cross-trains on each integration point; critical path documented; buffer week is Sprint 4 |

9. Cross-Document References

| Document | Doc ID | Purpose |
| --- | --- | --- |
| Deployment Plan | JASPER-DEPLOY-001 | Infrastructure, CI/CD pipeline, environment config, production go-live checklist |
| Testing Plan | JASPER-TEST-001 | Test strategy, pipeline tests, coverage targets, acceptance criteria, test completion report |
| Security Plan | JASPER-SEC-001 | Threat model, OWASP controls, Semgrep/Dependabot gates, RBAC audit requirements |

Document prepared by Edwin Olaez, PM & Lead QA/Security Engineer — Project Jasper | Deadline: August 3, 2026